# BYUMS BUSINESS PLAN GRADER

## Project Proposal & Investment Overview

Prepared by: Praise Enato & Felix Gbedemah

Date: February 19, 2026

Project Duration: 6 Months (MVP in 2 months, Full Product in 6 months)

────────────────────────────────────────────────────────────────────────────────

## 1. Executive Summary

We propose to build the BYUMS Business Plan Grader — an intelligent grading system that automatically reads, analyzes, and scores business plan submissions using advanced Artificial Intelligence.

Instead of spending hours manually reading through each business plan, the BYUMS Grader does it in under 30 seconds. It reads the submitted documents, evaluates them against a scoring rubric provided by BYUMS, and produces detailed written feedback with numerical scores — just like a human expert would, but faster and available 24/7.

The system handles:

PowerPoint business plan presentations

PDF/DOCX business plan documents

Video pitches (YouTube links)

Google Slides presentations

Bulk grading — grade dozens of submissions at once from a spreadsheet

The end product will be a private web-based platform for BYUMS to grade contestants' business plans, accessible from any browser on any device.

────────────────────────────────────────────────────────────────────────────────

## 2. The Problem We're Solving

### Current Pain Points

Grading business plans is currently a slow and inconsistent process:

| Challenge | Impact |
| --- | --- |
| Time-consuming | A single business plan takes 15–30 minutes to grade manually |
| Inconsistent | Different graders give different scores for the same submission |
| Not scalable | Grading 100+ submissions requires a large team |
| No instant feedback | Contestants have to wait days or weeks for results instead of getting instant feedback |
| Limited availability | Human graders aren't available 24/7 |

────────────────────────────────────────────────────────────────────────────────

## 3. Our Solution — What BYUMS Does

### Core Capabilities

The BYUMS Business Plan Grader is an AI-powered platform that:

1. Reads & Understands Submissions

Accepts business plans as PowerPoint slides, PDF/DOCX documents, video pitches, or Google Slides links

Extracts and understands all text, financial data, charts, and visual elements

For video pitches — watches the video, listens to the presentation, and evaluates delivery

2. Grades Using BYUMS's Rubric

Evaluates each submission against the scoring rubric provided by BYUMS

Users can also upload or customize rubrics to fit different evaluation needs

Each rubric area receives a score and detailed written feedback

3. Produces Detailed Feedback

Generates professional written feedback (500–1,000 words per submission)

Identifies specific strengths and weaknesses

Provides actionable suggestions for improvement

Assigns numerical scores with confidence ratings

4. Handles Bulk Grading

Upload a spreadsheet with dozens or hundreds of contestants' details

The system grades all submissions automatically — running multiple gradings simultaneously

Results can be downloaded as a spreadsheet for easy record-keeping

5. Provides Analytics & Reports

Dashboard showing score distributions, average grades, and trends

Downloadable reports (PDF/DOCX/spreadsheet) per submission or per batch

Historical data — compare performance across different competitions or time periods

### How It Works (In Simple Terms)

Step 1 → Upload a business plan (PowerPoint, PDF/DOCX, video link, or Google Slides)
Step 2 → Select or upload a grading rubric
Step 3 → The AI reads the entire submission and cross-references industry best practices
Step 4 → The system evaluates each rubric category and writes feedback
Step 5 → Results appear on screen within 30 seconds — scores, feedback, and suggestions
Step 6 → Download the results as a PDF/DOCX report or spreadsheet

────────────────────────────────────────────────────────────────────────────────

## 4. Development Timeline

### Overview: 6 Months, 4 Phases

| Phase | Timeline | What Gets Delivered |
| --- | --- | --- |
| Phase 1: Core Grading | Month 1 (Weeks 1–4) | AI grading engine for PowerPoint & PDF/DOCX submissions + basic web interface |
| Phase 2: Enhanced Features | Month 2 (Weeks 5–8) | Video pitch analysis, Google Slides support, bulk grading, quality benchmarking |
| Phase 3: Production Launch | Month 3 (Weeks 9–12) | User accounts, data storage, analytics dashboard, live deployment on the internet |
| Phase 4: Full Product | Months 4–6 (Weeks 13–24) | Advanced features, security hardening, contestant submission portal, final polish |

────────────────────────────────────────────────────────────────────────────────

### Phase 1: Core Grading System — Month 1

What you'll see at the end of this phase: A working website where you can upload a PowerPoint or PDF/DOCX business plan, and the AI will read it, grade it, and show you detailed scores and feedback.

#### Week 1: Foundation

| What We're Building | Hours |
| --- | --- |
| Setting up the project structure and AI engine connection | 16 |
| Building the document reader (understands PowerPoint & PDF/DOCX files) | 16 |
| Creating the data structures for rubrics, grades, and submissions | 16 |
| Designing & building the website layout, navigation, and branding | 16 |
| Setting up the design theme (colors, fonts, dark mode) | 16 |
| Week 1 Total | 80 hrs |

#### Week 2: Grading Engine

| What We're Building | Hours |
| --- | --- |
| Building the AI grading brain — the multi-step evaluation pipeline | 24 |
| Integrating BYUMS's rubric format into the grading system | 8 |
| Crafting the AI's grading instructions & evaluation criteria | 8 |
| Building the grading page — file upload, rubric selection, submit button | 16 |
| Building the results display — scores, feedback, and suggestions | 16 |
| Creating custom rubric upload/edit functionality | 8 |
| Week 2 Total | 80 hrs |

#### Week 3: Integration & Intelligence

| What We're Building | Hours |
| --- | --- |
| Connecting the website to the AI grading engine | 16 |
| Loading industry best practices into the knowledge base | 8 |
| Building the grading error handling & input validation | 12 |
| Building rubric file parser (reads rubrics from PDF/DOCX/spreadsheet) | 8 |
| Building the detailed results view (expandable feedback) | 8 |
| Mobile-friendly design adjustments | 8 |
| Connecting & testing all pieces together | 12 |
| Bug fixes from integration testing | 8 |
| Week 3 Total | 80 hrs |

#### Week 4: Testing & Polish

| What We're Building | Hours |
| --- | --- |
| Testing the grading engine with sample business plans | 20 |
| Quality checks — comparing AI grades with expected scores | 10 |
| Writing user documentation & setup guide | 8 |
| Visual polish — animations, loading indicators, transitions | 14 |
| Error messages & user-friendly notifications | 6 |
| Building the landing/home page | 14 |
| Final bug fixes | 8 |
| Week 4 Total | 80 hrs |

🏁 End of Month 1 — Core Grading Delivered A working system that can grade PowerPoint and PDF/DOCX business plans with AI-generated feedback and scores.

────────────────────────────────────────────────────────────────────────────────

### Phase 2: Enhanced Features — Month 2

What you'll see at the end of this phase: Everything from Phase 1, plus video pitch grading, Google Slides support, bulk grading from spreadsheets, and validated grading quality.

#### Week 5: Video & Google Slides Analysis

| What We're Building | Hours |
| --- | --- |
| YouTube video pitch analyzer — AI watches and evaluates video presentations | 20 |
| Google Slides support — reads slides directly from a shared link | 20 |
| Adding video & slides input fields to the grading page | 16 |
| Error handling for invalid or private links | 12 |
| Testing video and slides features | 12 |
| Week 5 Total | 80 hrs |

#### Week 6: Grading Improvements

| What We're Building | Hours |
| --- | --- |
| Adding video analysis results to the grading feedback | 18 |
| Adding slide design quality analysis to the feedback | 10 |
| Grading audit trail (records every grading step for transparency and accountability) | 12 |
| Grading history page — view all past grades, search, filter | 16 |
| In-app notification system (alerts when grading is complete) | 12 |
| Testing all features together | 12 |
| Week 6 Total | 80 hrs |

#### Week 7: Bulk/Mass Grading

| What We're Building | Hours |
| --- | --- |
| Mass grading engine — upload a spreadsheet, grade all entries at once | 22 |
| Spreadsheet reader (understands CSV and Excel formats) | 12 |
| Simultaneous grading — processes 3 submissions at the same time for speed | 10 |
| Mass grading page — upload spreadsheet, preview entries, track progress | 16 |
| Results view — summary stats, color-coded scores, downloadable results | 14 |
| Export results as spreadsheet | 6 |
| Week 7 Total | 80 hrs |

#### Week 8: Quality Assurance

| What We're Building | Hours |
| --- | --- |
| Grading accuracy benchmarking — testing against human expert grades | 18 |
| Optimizing AI grading instructions for better accuracy | 10 |
| Measuring grading speed & cost per submission | 12 |
| Website usability audit & fixes | 16 |
| Mobile responsiveness testing & fixes | 8 |
| Full end-to-end testing of all features | 8 |
| Demo preparation | 8 |
| Week 8 Total | 80 hrs |

🏁 End of Month 2 — MVP Delivery The product can now grade PowerPoints, PDF/DOCX documents, video pitches, and Google Slides. It supports bulk grading from spreadsheets. Grading quality has been validated against human experts.

────────────────────────────────────────────────────────────────────────────────

### Phase 3: Production Launch — Month 3

What you'll see at the end of this phase: The platform is live on the internet with user accounts, saved data, analytics, and professional deployment.

#### Week 9: User Accounts & Login

| What We're Building | Hours |
| --- | --- |
| Google & email login integration (one-click sign-in) | 18 |
| User account system — registration, login, profile management | 16 |
| Account security — password protection, session management | 12 |
| Admin vs. regular user permissions | 10 |
| Login & signup page design | 12 |
| User settings page | 12 |
| Week 9 Total | 80 hrs |

#### Week 10: Data Storage & Management

| What We're Building | Hours |
| --- | --- |
| Database design — storing users, rubrics, submissions, and grades | 18 |
| Database setup & connection | 12 |
| Save & retrieve grades (no more lost data) | 14 |
| Custom rubric saving — users can save and reuse their rubrics | 10 |
| Submission management page — view, re-grade, or delete past submissions | 14 |
| Data table features — sorting, filtering, pagination | 12 |
| Week 10 Total | 80 hrs |

#### Week 11: Analytics Dashboard

| What We're Building | Hours |
| --- | --- |
| Analytics calculations — averages, distributions, trends | 20 |
| Analytics dashboard page — charts, graphs, key metrics at a glance | 20 |
| Score distribution charts — see how submissions performed overall | 10 |
| Filter controls — view analytics by date range, business type, rubric | 8 |
| Export & download features — spreadsheets, PDF/DOCX reports | 14 |
| Dashboard visual polish | 8 |
| Week 11 Total | 80 hrs |

#### Week 12: Live Deployment

| What We're Building | Hours |
| --- | --- |
| Setting up the production server (cloud hosting) | 14 |
| Configuring the web server & security certificates (HTTPS) | 10 |
| Automated update system — new improvements go live seamlessly | 12 |
| System health monitoring page | 10 |
| Performance testing — simulating multiple users at once | 14 |
| Deployment documentation & troubleshooting guide | 12 |
| Verifying all features work on the live site | 8 |
| Week 12 Total | 80 hrs |

🏁 End of Month 3 — Live Deployed Platform The platform is live on the internet with user accounts, saved data, a full analytics dashboard, and professional hosting.

────────────────────────────────────────────────────────────────────────────────

### Phase 4: Full Product — Months 4–6

What you'll see at the end of this phase: A polished, secure, and scalable private grading platform ready for BYUMS to grade contestants at scale.

#### Weeks 13–14: Advanced Grading Features (160 hours)

| What We're Building | Hours |
| --- | --- |
| Rubric comparison tool — compare grades across different rubrics side-by-side | 28 |
| Custom grading style — customize how the AI evaluates and writes feedback | 24 |
| Grading consistency checker — grade the same plan multiple times to verify accuracy | 24 |
| User settings expansion — preferences, notification settings, defaults | 20 |
| Contestant results summary — generate polished summary reports per contestant | 24 |
| Documentation & user guide updates | 20 |
| Full feature testing | 20 |
| Weeks 13–14 Total | 160 hrs |

#### Weeks 15–16: Security & Performance (160 hours)

| What We're Building | Hours |
| --- | --- |
| Speed optimization — faster page loads, smarter data caching | 24 |
| Security hardening — protecting user data, preventing unauthorized access | 24 |
| Usage limits — preventing abuse, fair usage policies | 16 |
| Error tracking & alerting — automatic alerts when something goes wrong | 16 |
| Smooth multi-tasking — long grading jobs run while users continue working | 16 |
| Website speed optimization — faster loading on all devices | 20 |
| Accessibility — making the platform usable for people with disabilities | 16 |
| Cross-browser testing — Chrome, Safari, Firefox, Edge | 16 |
| Bug fixing sprint | 12 |
| Weeks 15–16 Total | 160 hrs |

#### Weeks 17–20: Contestant Submission Portal & Integrations (320 hours)

| What We're Building | Hours |
| --- | --- |
| Contestant submission portal — a private page where contestants submit their plans directly | 36 |
| Automatic email notifications — contestants receive confirmation when submission is received | 28 |
| Automatic notification to BYUMS admins when new submissions arrive | 20 |
| Submission tracking dashboard — see all incoming submissions, status, and grading progress | 28 |
| Contestant results page — contestants can view their grade and feedback after grading | 24 |
| Bulk notification system — email all contestants their results at once | 20 |
| Interactive help documentation & user guides | 26 |
| Usage tracking & reporting — see grading volume, peak times, and submission trends | 20 |
| Cost optimization — reducing AI costs while maintaining quality | 16 |
| Full integration testing | 26 |
| Buffer for unforeseen tasks & client feedback | 76 |
| Weeks 17–20 Total | 320 hrs |

#### Weeks 21–24: Final Polish & Launch (320 hours)

| What We're Building | Hours |
| --- | --- |
| Professional landing page — polished homepage with product overview | 28 |
| First-time user onboarding guide — interactive tutorial for new users | 20 |
| Email template design — welcome emails, grade notifications, submission confirmations | 14 |
| Server scaling — preparing for high traffic during competition periods | 22 |
| Load testing — simulating 50+ simultaneous users to ensure stability | 16 |
| Full product testing — every feature, every page, every scenario | 24 |
| Beta testing with BYUMS team & feedback implementation | 24 |
| Bug fixes & visual polish | 40 |
| Final documentation — complete user guide, admin guide | 20 |
| Post-launch monitoring — first 48 hours of live support | 16 |
| Lessons learned & future improvement planning | 8 |
| Final cost & usage audit | 12 |
| Buffer for unforeseen tasks & client feedback | 76 |
| Weeks 21–24 Total | 320 hrs |

🏁 End of Month 6 — V1 Launch Production-ready private grading platform with all features, security hardening, contestant submission portal, and professional polish. Ready for BYUMS to run competitions.

────────────────────────────────────────────────────────────────────────────────

## 5. Hours Summary

### By Phase

| Phase | Duration | Total Hours |
| --- | --- | --- |
| Phase 1: Core Grading | Month 1 (Weeks 1–4) | 320 hours |
| Phase 2: Enhanced Features | Month 2 (Weeks 5–8) | 320 hours |
| Phase 3: Production Launch | Month 3 (Weeks 9–12) | 320 hours |
| Phase 4: Full Product | Months 4–6 (Weeks 13–24) | 960 hours |
| TOTAL | 6 months | 1,920 hours |

### By Developer

| Team Member | Weekly Hours | Total Weeks | Total Hours |
| --- | --- | --- | --- |
| Praise Enato — AI Engineer | 40 hours/week | 24 weeks | 960 hours |
| Felix Gbedemah — AI Engineer | 40 hours/week | 24 weeks | 960 hours |

### What Those Hours Cover

| Activity Area | Estimated Hours | Share of Total |
| --- | --- | --- |
| AI Grading Engine & Intelligence | 420 hours | 22% |
| Website Design & User Interface | 440 hours | 23% |
| Testing & Quality Assurance | 280 hours | 15% |
| Data Storage & User Management | 200 hours | 10% |
| Server Setup & Deployment | 140 hours | 7% |
| Documentation & User Guides | 120 hours | 6% |
| Design & Visual Polish | 160 hours | 8% |
| Buffer (Client Feedback & Adjustments) | 160 hours | 9% |
| TOTAL | 1,920 hours | 100% |

────────────────────────────────────────────────────────────────────────────────

## 6. Team

### Development Team

| Role | Person | Responsibilities |
| --- | --- | --- |
| AI Engineer | Praise Enato | AI grading engine, grading accuracy, system architecture, server management, integration |
| AI Engineer | Felix Gbedemah | Website design & development, user interface, user experience, visual polish, testing |

Both team members are AI Engineers with hands-on experience building AI-powered applications, including prior work on a similar grading system. The team brings expertise in:

Building AI-powered evaluation systems

Designing intuitive web interfaces

Working with industry-leading AI models

Deploying web applications to production

Document processing and natural language understanding

────────────────────────────────────────────────────────────────────────────────

## 7. Cost Estimation

### A. Development Team Costs

| Item | Monthly Rate | Duration | Total |
| --- | --- | --- | --- |
| Praise Enato — AI Engineer | $1,000/month | 6 months | $6,000 |
| Felix Gbedemah — AI Engineer | $1,000/month | 6 months | $6,000 |

### B. AI Service Costs (Pay-As-You-Go)

The AI services charge per submission — you only pay for what you use. There are no monthly subscriptions.

| AI Service | What It Does | Cost Per 1,000 Submissions |
| --- | --- | --- |
| Primary Grading AI | Reads and grades text-based business plans | $5 – $10 |
| Vision AI | Analyzes video pitches and slide designs | $16 – $20 |

Cost Examples:

| Scenario | Submissions | Text-Only Cost | With Video Analysis |
| --- | --- | --- | --- |
| Small competition | 100 submissions | $0.50 – $1.00 | $2.10 – $3.00 |
| Medium competition | 500 submissions | $2.50 – $5.00 | $10.50 – $15.00 |
| Large competition | 1,000 submissions | $5.00 – $10.00 | $21.00 – $30.00 |

### C. Infrastructure & Hosting Costs

| Item | 6-Month Total | Notes |
| --- | --- | --- |
| Cloud Server Hosting | $0 – $180 | Free tier for the first few months, then ~$25/month |
| Custom Domain Name | ~$18 | Professional web address (e.g., byums.com) |
| SSL Security Certificate | $0 | Free (industry standard) |
| Code Repository | $0 | Free tier |
| Error Monitoring | $0 | Free tier |
| Infrastructure Total | $18 – $198 |  |

### D. Total Project Budget

| Category | Low Estimate | High Estimate |
| --- | --- | --- |
| Development Team (6 months) | $12,000 | $12,000 |
| AI Services (estimated 2,000 submissions during development & testing) | $15 | $35 |
| Infrastructure & Hosting (6 months) | $18 | $198 |
| Miscellaneous & Contingency (10%) | $1,203 | $1,223 |
| TOTAL PROJECT COST | $13,236 | $13,456 |

Bottom line: The total investment to build BYUMS Business Plan Grader from start to launch is approximately $13,250 – $13,500.

────────────────────────────────────────────────────────────────────────────────

## 8. What You Get at Each Milestone

| Milestone | When | What's Delivered |
| --- | --- | --- |
| 🏗️ Working Prototype | End of Month 1 | Upload a business plan → Get AI-generated grades & feedback |
| 🚀 MVP | End of Month 2 | + Video grading, Google Slides, bulk grading, quality validation |
| 🔐 Live Platform | End of Month 3 | + User accounts, saved data, analytics dashboard, live on the internet |
| 🔒 Hardened Product | End of Month 4 | + Advanced features, security hardening, performance optimization |
| 📩 Contestant Portal | End of Month 5 | + Contestant submission portal, email notifications, submission tracking |
| 🎯 Launch-Ready | End of Month 6 | Fully polished, tested, and ready for BYUMS competitions |

────────────────────────────────────────────────────────────────────────────────

## 9. Key Features Summary

| Feature | Description |
| --- | --- |
| AI-Powered Grading | Reads and grades business plans in under 30 seconds |
| Multi-Format Support | PowerPoint, PDF/DOCX, YouTube video, Google Slides |
| Custom Rubrics | Upload BYUMS's own rubric or create custom scoring criteria |
| Video Pitch Analysis | AI watches video presentations and evaluates delivery & content |
| Slide Design Analysis | Evaluates visual quality and professionalism of slides |
| Bulk/Mass Grading | Grade dozens of submissions at once from a spreadsheet |
| Detailed Feedback | 500–1,000 words of actionable written feedback per submission |
| User Accounts | Login, save history, manage submissions |
| Analytics Dashboard | Charts, trends, score distributions, and exportable reports |
| Contestant Submission Portal | Private portal where contestants submit their plans directly |
| Email Notifications | Automatic emails when submissions are received and graded |
| PDF/DOCX Reports | Downloadable grade reports for each submission |
| Mobile Friendly | Works on phones, tablets, and desktops |
| Dark Mode | Easy on the eyes for extended use |

────────────────────────────────────────────────────────────────────────────────

We are confident that the BYUMS Business Plan Grader will dramatically improve the speed, consistency, and quality of business plan evaluations. With a total investment of approximately $13,250 – $13,500 and a 6-month timeline, we will deliver a production-ready private platform that grades business plans faster and more consistently than manual evaluation. We look forward to building this with you. — Praise Enato & Felix Gbedemah